## Slide 1
Cloud Maturity Assessment Tool
Build-first approach (no AI) · Product is ready· AI integration in future phase
AXA ASIA CLOUD BROKER
Weekly Update
Automation Projects · May 2026
EXTERNAL
IN PROGRESS
CONFIDENTIAL – INTERNAL USE ONLY
IN PROGRESS
Cost Estimator
New UI/UX· Other products added (MPI, NAS, POD)
Pricing update feature on portal·
INTERNAL

## Slide 2: Automation Project Updates
Cost Estimator/Cloud Maturity Assessment
IN PROGRESS
TOOL UPDATES
Create new subscription (non-prod and prod) under AXA 365 tenant
(7 July-9 July)
Apply security fix/recommendation provided by Balaji
(2-10 July )
Deploy to new non-prod subscription
(9 July-10 July)
Provide new link to Tayisiya Tarasova to add for Cloud Broker Home Page
(13 July)
Engage security to perform full review
(13-19 July)
24 Mar
Other Automation Task
IN PROGRESS
UPDATES
ACTIONS Items
1. Current status: completed
New subscription created
Resource deployment completed
Estimator deployed and enabled on AXA 365 tenant
Vnet creation completed
In progress - fqdn creation and certificate for custom domain
-DNS record RITM10861216
Milestone | Timeline | Status
Subscription creation (AXA 365 tenant) | 10th July | Completed
Apply security fixes & recommendations | 2–10 July | In Progress
Deploy to non-prod subscription | 9 July – 10 July | Scheduled
Share live link with Taisiya | 13 July | Scheduled
Full security review | 13–19 July | Scheduled
Azure Monitoring and Notification Solution (SPN, Orphaned disk, Keyvault)
Scope: Tech Asia Tenant
AXA Hong Kong Nonprod and Preprod subscription (Completed)
AXA Hong Kong Production subscription (Completed)
Other items in progress
HLD / LLD
Functional Documentation
Technical Documentation
Resource Inventory
Code Repository and CI/CD Chain

## Slide 3
MPI CALCULATOR → AXA CLOUD COST ESTIMATOR |  |  |  |  |  |  |  |  |  | 
PROJECT PHASE | Dec 2025 Closing with V1 (MPI Calculator v1) | JAN 2026 Dual Cloud Enhancement | FEB 2026 Dual Cloud Enhancement | MAR 2026 Scope Expansion (Rename Decision) | EARLY APR 2026 Rebuild Decision | MID APR 2026 AXA Cloud Estimator Implementation | APR 17, 2026 ★ Last MVP | MAY 2026 | JUNE 2026 | JULY, 2026 ★ Go-live
MPI Calculator v1 (Dec 2025) | ✓ MPI Calculator concept ✓ Azure Pricing API integration ✓ Vanilla HTML + Bootstrap + JS ✓ App Service: z-mpi-calc-project-app01 ✓ Azure DevOps pipeline created ✓ VM / SKU selection by region ✓ Hourly & monthly cost output ✓ 30% MPI support surcharge ✓ Excel export (SheetJS) ✓ Dev / staging slot deployment | ✓ Azure + AWS dual-cloud in one UI ✓ Static JSON price files (~15 MB) ✓ AWS EBS disk type support ✓ OS-specific pricing (Win / Linux) ✓ Branch-based pipeline YAML conditionals ✓ Save / load calculations (localStorage) ✓ Windows Server 2022 support added | ✓ Full codebase review session (Feb 9) ✓ Pricing data validation (Azure + AWS JSON files) ✓ Pipeline YAML slot conditionals stabilised ✓ No new features — tool in stable state post-dual-cloud | ✓ NAS team call — 24 Mar 2026 ✓ Presented current tool to NAS team ✓ Fileshare PO: Priyadarshini ✓ Gathered NAS charging requirements ✓ Decision: build unified 'AXA Cloud Estimator' ✓ Scope: MPI + NAS + POD + Terraform WS ✓ Shared with Olivier; to present to Nicolas | ✓ Scrap vanilla HTML/JS entirely ✓ Rebuild: React + Vite SPA ✓ Azure Functions Node.js v4 backend ✓ Entra ID SSO (existing app registration) ✓ 4 Table Storage tables: Products / Estimates / AuditLog / UserRoles ✓ Reuse existing App Service + slots ✓ Azure live pricing API (approved regions) ✓ AWS pricing remains static JSON | ✓ 4-product estimator: MPI / NAS / POD / TF WS ✓ Tabs: Estimator / Pricing Panel / IAM ✓ Roles: super_admin / pricing_admin / user ✓ Flat rate-card model (no per-SKU lookup) ✓ Pricing admin scoped per product ✓ Per-user estimates; super_admin sees all ✓ Pricing audit log (old→new, user, timestamp) ✓ PDF + CSV export ✓ Dark / light theme toggle | ✓ MPI cost logic fully refined ✓ Per-VM charge multipliers confirmed ✓ FX rate (USD → EUR) applied ✓ License key resolution (Win / Linux / SQL / Oracle / JBoss) ✓ Middleware + DB2 pattern flags ✓ Architecture fully aligned with CMA stack ★ Last active session: Apr 27, 2026 | ✓ Present to Oliver: May 13 | ✓ Deploy to global tenant | ★ Target to go-live
CLOUD MATURITY ASSESSMENT PLATFORM (CMA) |  |  |  |  |  |  |  |  |  | 
PROJECT PHASE | FEB – MAR 2, 2026 Concept | MAR 25–26, 2026 Presentations | MAR 2026 Pivot + Design | APR 8, 2026 v1 — Full Build | APR 8–14, 2026 v2 → v4 | APR 14–16, 2026 v5 → v8 | APR 17, 2026 ★ v9 — Last MVP | MAY, 2026 | JUNE, 2026 | JULY, 2026 ★ Go-live
CMA Platform (Feb – Apr 2026) | ✓ Cloud Adoption Journey tool concept ✓ Reference deck: Asia CB CMA Platform.pptx ✓ AI-generated questions via RAG ✓ Azure OpenAI + Azure AI Search ✓ Confluence + Azure/AWS doc ingestion ✓ Agentic dynamic follow-up logic ✓ 5-section assessment structure ✓ Footprint / Migration / Team / Challenges | ✓ AI Use Case Collection Call — 25 Mar ✓ Presented to larger audience ✓ Positive reception across teams ✓ Olga sync — 26 Mar ✓ Framework inputs aligned with Olga ✓ GO Strategy meeting (Ankur + Randolphe) ✓ CMA well-received by leadership ✓ Action: PEPPS demand for SecureGPT creds ✓ AI Use Case ID Card update pending | ✓ Pivot: adoption → operational maturity ✓ Excel v0.2 — 37 questions, 5 categories ✓ Platform branching: MPI / POD / OpenPaaS ✓ Scoring: Beginner / Intermediate / Advanced ✓ AI dropped — structured form UX instead ✓ Stack: React + Functions + SWA + Entra ID | ✓ React frontend + Azure Functions Node.js v4 ✓ 4 Table Storage tables (users / entities / assessments / settings) ✓ Azure Static Web Apps + Entra ID SSO ✓ Chat-style assessment UX ✓ Radar chart + section score bars ✓ Per-section recommendations ✓ PDF export + Azure DevOps pipeline ✓ Roles: superadmin / admin / user | ✓ v2: Initial deploy bug fixes ✓ v3: backend/package.json main field locked ✓ v3: EnableWorkerIndexing flag added ✓ v3: Auth middleware — userDetails fallback ✓ v3: CORS preflight fix (full page nav) ✓ v3: responseOverrides.401 removed ✓ v3: Presented to Sureen and gathered feedback on improvements ✓ v4: Section weights in Settings tab ✓ v4: Progress bar redesign (5-section) ✓ v4: Questions CRUD tab ✓ v4: /api/questions backend endpoint | ✓ v5: Per-product scoring + separate submissions ✓ v6: Dark / light mode toggle (moon / sun) ✓ v6: Expandable recommendation cards ✓ v6: Maturity legend (Green / Amber / Red) ✓ v6: Multi-product aggregate dashboard ✓ v7: Infrastructure remediations consolidated ✓ v8: filterApplicableQuestions updated ✓ v8: product field fix — incomplete (normalization map still dropping product field) | ✓ Root cause fixed: product field preserved in AssessmentRun normalization map ✓ Platform-specific question filtering works ✓ PDF rewritten: per-product sections ✓ questionAppliesToProduct helper added ✓ Demo speaking notes drafted (7–8 min) ✓ Management presentation confirmed ✓ Code has been share with security ★ Last active session: Apr 21, 2026 | ✓ Waiting complete report/ findings for security | ✓ Deploy to global tenant | ★ Target to go-live